## BD CX DMU Requirements
Ref | Function | Business Requirement | Requirement Type | BC Capability | Status | Details | Phase | Total | Done | Not Done | Deployed | Stepped Down
1 | Lead Management | [7 empty] | 0 | 21 | 0 | 0
1.01 | Lead Management | Ability to create new lead on the go | Initial requirement | Out-of-the-box functionality | Not Done
1.02 | Lead Management | Ability to bulk upload leads using the excel file | Initial requirement | Customization required | Not Done
1.03 | Lead Management | Ability to create new leads from the mobile and sales app | Initial requirement | Out-of-the-box functionality | Not Done
1.05 | Lead Management | Ability to create leads originated from social media (Twitter, Facebook, Instagram, etc) | Initial requirement | Integration required | Not Done
1.06 | Lead Management | Ability to specify lead source | Initial requirement | Out-of-the-box functionality | Not Done
1.07 | Lead Management | Ability to specify lead rating | Initial requirement | Out-of-the-box functionality | Not Done
1.08 | Lead Management | Ability to specify customer lead referral linked to existing account | Initial requirement | Customization required | Not Done
1.09 | Lead Management | Ability to specify revenue projected information about lead | Initial requirement | Customization required | Not Done
1.1 | Lead Management | Ability to specify products per lead | Initial requirement | Customization required | Not Done
1.11 | Lead Management | Ability to specify lead type (employer/employee) | Initial requirement | Customization required | Not Done
1.12 | Lead Management | Ability to specify the marital status of a lead | Initial requirement | Customization required | Not Done
1.13 | Lead Management | Ability to specify lead status | Initial requirement | Out-of-the-box functionality | Not Done
1.14 | Lead Management | Ability to assign leads to queue based on the business logic when lead is getting created from the application | Initial requirement | Customization required | Not Done
1.15 | Lead Management | Ability to manually assign leads to a user or a team | Initial requirement | Out-of-the-box functionality | Not Done
1.16 | Lead Management | Ability to view information about lead activity/inactivity | Initial requirement | Out-of-the-box functionality | Not Done
1.17 | Lead Management | Ability to convert lead into corresponding Employee/Employer account based on information entered | Initial requirement | Customization required | Not Done
1.18 | Lead Management | Ability to convert lead into opportunity with all lead information | Initial requirement | Out-of-the-box functionality | Not Done
1.19 | Lead Management | Ability to indicate & recognize State/Region and ARMP branch | Additional requirement | Integration required | Not Done
1.21 | Lead Management | Ability to invalidate special characters i.e (-, . , ? /@ £) on Name field | Additional requirement | Integration required | Not Done
1.22 | Lead Management | DOB validation on system i.e Age should be equal or greater than 18 | Additional requirement | Integration required | Not Done
1.23 | Lead Management | System ability to specify preferred mode of communication and whether prospect wish to receive marketing materia or not | Additional requirement | Integration required | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
2 | Account Management | [6 empty] | 9 | 0 | 9 | 0 | 0
Ref | Function | Business Requirement | Requirement Type | CRM Capability | Status | Details | Phase
2.01 | Account Management | Ability to call up client's summary profile page showing - Full Name, DOB, Age, Date of Registration, Segmentation, Gender, Nok, Last employer, Current employer, last period of remittance/amount, Cumulative Gain, Net contribution, Total Contribution, AVC, last update and DR status | Initial requirement | Customization required | Not Done
2.02 | Account Management | Ability to view Employer's account with a summary of showing - Employer Name, previous name (where applicable), Total client count, tier, contact details, last period of remittance, funding status (fully funded/partially funded), unprocessed remittance if any, unfunded accounts if any. | Initial requirement | Customization required | Not Done
2.03 | Account Management | System ability to allow Users select employers/clients to be engaged at a time and converted to a call plan. Call plan to be visible to TL | Initial requirement | Customization required | Not Done
2.04 | Account Management | Ability to differentiate remittance received from an employer to remmittance captured on the client account card, update should be initiated and remittance flagged. | Initial requirement | Integration required | Not Done
2.05 | Account Management | Ability to notify clients periodically with useful tips | Initial requirement | Customization required | Not Done
2.06 | Account Management | Ability to allow Employer contacts to receive communication for their support monthly; highlighting how long account has been managed, amount received for the period status of remittance, unfunded if any and industry update. Employees' compliance to regulatory requirement e.g. DR | Initial requirement | Customization required | Not Done
2.07 | Account Management | Ability to ensure Clients receive thank you message highlighting how long they have been registered, net contribution, cumulative gain so far, AVC balance (or AVC pitch where client is yet to sign up), details of assigned BDE and client's achievement for the period | Initial requirement | Customization required | Not Done
2.08 | Account Management | Ability to ensure Users are able to set up meetings and a reminder to be sent to user an hour before the meeting with TL copied and sequent escalation for meetings not attended | Initial requirement | Customization required | Not Done
2.09 | Account Management | Ability to ensure after completion of a session users should be able to generate Post Call Memo by providing employer name, date event, facilitators, number of attendees, Q&A, action plan and areas of discussion | Initial requirement | Customization required | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
3 | Function | [6 empty] | 10 | 0 | 10 | 0 | 0
3.01 | Client Onboarding | Ability to create various account schemes on application and on the go; MPS, CPS, Cross Border, TPIN | Initial requirement | Out-of-the-box functionality | Not Done
3.02 | Client Onboarding | Ability to commence TAT measurement from when onboarding card is opened TAT should be measure and captured on the account card across the entire workflow process end-to-end" | Initial requirement | Customization required | Not Done
3.03 | Client Onboarding | Ability to integrate with all onboarding applications and should be able to share status and details of an account and ongoing account creation for both staff and clients | Initial requirement | Out-of-the-box functionality | Not Done
3.04 | Client Onboarding | Ability to specify account schemes i.e Users should be able to indicate account scheme which should drive the account data model: MPS, CPS, TPIN, Cross Border | Initial requirement | Out-of-the-box functionality | Not Done
3.05 | Client Onboarding | Ability to identify and track customers that are Next of Kin/Beneficiaries: During account creation or for existing account (migrated) where the next of kin/beneficiary is client the system to flag and reference same | Initial requirement | Out-of-the-box functionality | Not Done
3.06 | Client Onboarding | Ability to track the Lead owner at Account level : The system should be able to track the user that initiated lead conversion when Account is getting created | Initial requirement | Out-of-the-box functionality | Not Done
3.07 | Client Onboarding | Ability to capture the Account creation status along the creation workflow: Application should be able to set the Account status automatically i.e. pending" "approved" depending on the stage of the workflow the process has reached. | Initial requirement | Customization required | Not Done
3.08 | Client Onboarding | Ability to choose client communication preference i.e. • Email • Phone • Visit • Letters • Contact only through RM Also, where receive marketing materials option had been selected, this should be tracked and updated by the system | Initial requirement | Out-of-the-box functionality | Not Done
3.09 | Client Onboarding | Ability to input client/dependent's key event se.g Users should be able to enter wedding anniversary and birthday information for clients and dependents | Initial requirement | Customization required | Not Done
3.1 | Client Onboarding | Ability to select customer referral source on Account detail page which may come from Lead conversion or new Account creation in the Application. | Initial requirement | Customization required | Not Done
3.11 | Client Onboarding | Ability to select the related employer for an employee account i.e link/ show relationship between an Individual Account (Employee) and a Parent Account (Employer) |  |  | Not Done
3.12 | Client Onboarding | Ability to view records that are yet to get PINs across all onboarding systems and supervisor should for all Team Members |  |  | Not Done
3.13 | Client Onboarding | Ability to indicate client's previous employer during onboarding and when DR/Update takes place. The system to show value on the account card |  |  | Not Done
3.14 | Client Onboarding | Ability to to detect existing record already created either as account, contact, lead, etc using either or all of the following field validation: First Name, Last Name, DOB, Mobile Number, Email, NIN or BVN |  |  | Not Done
3.15 | Client Onboarding | Abillity for TL to receive notification including view for user and TL to see all generated account across all onboarding systems when an account has been approved by PENCOM and PIN generated. |  |  | Not Done
3.16 | Client Onboarding | Account should be auto mapped to BDEs mapped to employer as RM |  |  | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
4 | Employer Onboarding | [6 empty] | 2 | 0 | 2 | 0 | 0
4.01 | Employer Onboarding | Ability to create various employer account schemes - AES defined benefit, AES defined contribution, CPS and linked to various individual clients |  |  | Not Done
4.02 | Employer Onboarding | Ability for System to auto flag when an existing client or lead is created as an employer contact during onboarding and data migration |  |  | Not Done
4.03 | Employer Onboarding | Ability to apply segmentation rule as per Tier and subsequently Funded, Unfunded, Partially Funded, Active and Inactive, when an employer account is created. |  |  | Not Done
4.04 | Employer Onboarding | Ability to view Employers’ accounts with a summary of total customers, account tier, sector classification, industry, number of funded/unfunded accounts and ability to view partially funded accounts. Information must be available at all times. Where account is migrated, system should also auto populate |  |  | Not Done
4.04 | Employer Onboarding | Functionality to ensure Total client is consistent with count on the employer account form. Where a client changes employer and remittance is received from another employer the count should be updated and such record removed from employer client list |  |  | Not Done
4.05 | Employer Onboarding | Ability to integrate with all onboarding applications and feature to share status and details of an account and ongoing account creation for both staff and clients. |  |  | Not Done
4.06 | Employer Onboarding | Ability to ensure Employer contact details is captured including DOB, Marital Status, Wedding Anniversary (where applicable), Date of Current employment, ARMP client "Yes or No" |  |  | Not Done
4.07 | Employer Onboarding | Ability for TL to receive notification when DMU uploads employer code after validation and provision of code by PENCOM, including view for users and TL to see all generated account across all onboarding systems. |  |  | Not Done
4.08 | Employer Onboarding | Once employer codes are uploaded, the employer contacts should be notified via email (with BDE copied) and via SMS (contacts only) |  |  | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
5 | Remittance Management | [6 empty] | 2 | 0 | 2 | 0 | 0
5.01 | Remittance Management | Ability for assigned BDE to receive notification with details of remittances, where CPU is not able to process part or entire remittance due to various unprocessed monies issue. TL to be copied | Initial requirement | Out-of-the-box functionality | Not Done
5.02 | Remittance Management | Ability to auto generate evidence of remittance in predefined template format which can be sent as email directly to employers. Where request is for specific PINs, PIN details should be supplied with period required and document is generated with appended signature appended. | Initial requirement | Out-of-the-box functionality | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
6 | Data and Reporting | [6 empty] | 5 | 0 | 5 | 0 | 0
6.01 | Data and Reporting | Ability to provide real time data to client facing apps such as WiT, ARM Engage, Sales toolkit etc. | Initial requirement | Customization required | Not Done
6.021 | Data and Reporting | Ability to create, reallocate and deactivate agent profiles | Initial requirement | Customization required | Not Done
6.03 | Data and Reporting | Ability to reallocate accounts | Initial requirement | Customization required | Not Done
6.04 | Data and Reporting | System integration between the sales and HR modules for agent creation and performance tracking | Initial requirement | Customization required | Not Done
6.05 | Data and Reporting | Ability to connect with Officelime to automatically pull performance numbers during appraisals | Initial requirement | Customization required | Not Done
| DMU Requirement | [6 empty] | Total | Done | Not Done | Deployed | Stepped Down
7 | PIN Generation | [6 empty] | 4 | 0 | 4 | 0 | 0
7.01 | PIN Generation | Ability for PIN generation request to flow to DMU from BD/CX |  |  | Not Done
7.02 | PIN Generation | Abaility to enable processor review documents for accuracy before forwarding to Pencom |  |  | Not Done
7.03 | PIN Generation | Configuration and implementation of accurate date stamp with COB & Public holidays factored. |  |  | Not Done
7.04 | PIN Generation | Implementation of automated EOD reconciliation system to reconcile and update records on ARMP and ECRS systems. |  |  | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
8 | Data Recapture | [6 empty] | 1 | 0 | 1 | 0 | 0
8.01 | Data Recapture | Need to resubmit document in the event of erroneous rejection caused by downtime during processing. | Initial requirement | Customization required | Not Done
8.02 | Data Recapture | A view to be created on NAV tagged 1. Records with Partial Documentation (RSA)2.Records with Partial Documentation (DR). This will include the agent name and code of the profiler. |  |  | Not Done
8.03 | Data Recapture | Approved DR by PenCom should automatically be approved to NAV without human intervention. |  |  | Not Done |  |  | Total | Done | Not Done | Deployed | Stepped Down
9 | Record Update | [6 empty] | 1 | 0 | 1 | 0 | 0
9.01 | Record Update | Integration of ECRS with Navision to enable automation of approved record update on Nav. | Initial requirement | Integration required | Not Done
9.02 | Record Update | System ability to carry out document merge, Manual compression of merged PDF supporting documents above 1.2MB, This should be auto compressed to specified size of 1.1MB or below at the point of approval (This is an internal process) |  |  | Not Done |  |  | Total | Done | Not Done | Deployed | Stepped Down
9.03 | Record Update | CX should be enabled to input clients details for all requests and submitted for DMU's approval. |  |  | Not Done
9.04 |  | System ability to prevent Rejected records that have been corrected from returning to DM with the date of creation instead of recent submission date |  |  | Not Done
9.05 | Record Update | DM only validate with the supporting documents and either approve or rejects. |  |  | Not Done
10 | Archive Process | [6 empty] | 2 | 0 | 2 | 0 | 0
10.01 | Archive Process | Physical forms should be generated for all mobile device registration. |  |  | Not Done
10.02 | Archive Process | Automation of library number at the point of PIN generation for easy identification of documents. |  |  | Not Done
10.03 | Archive Process | Implementation of platform to upload all documents on e-libary |  |  | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
11 | Flagging and Blocking of PIN | [6 empty] | 11 | 0 | 3 | 0 | 0
11.01 | Flagging and Blocking of PIN | Transactions are not to be carried out on blocked PINs except for flagged PINs. | Initial requirement | Integration required | Not Done
12.02 | Flagging and Blocking of PIN | Ability to update social media handles of customers and non-ARMP customers | Initial requirement | Integration required | Not Done
11.02 | Flagging and Blocking of PIN | Ability to flag client details for those that wants to deactivate the sms alert, this to be activated on Record update workflow. |  |  | Not Done
| CX Requirement | [6 empty] | Total | Done | Not Done | Deployed | Stepped Down
13 | 25% Benefit application | [6 empty] | 7 | 0 | 7 | 0 | 0
12.01 | 25% Benefit application | Ability to reupload document for individual document fields. | Initial requirement | Out-of-the-box functionality | Not Done
12.02 | 25% Benefit application | All document fields should be available after upload of partial documents. | Initial requirement | Out-of-the-box functionality | Not Done
12.03 | 25% Benefit application | Ability to make some required fields should be made optional. | Initial requirement | Out-of-the-box functionality | Not Done
12.04 | 25% Benefit application | Ability to flag Multiple benefit request logged for Client on workflow to avoid duplicate submission for a single client. | Initial requirement | Out-of-the-box functionality | Not Done
12.05 | 25% Benefit application | Ability to auto populate document fields with existing documents. | Initial requirement | Integration required | Not Done
12.06 | 25% Benefit application | Ability for the system to enhance resolution of documents sent by CX and same received at BAU's end to address issues of blurry images. As the current system in use does not make provision for this. | Additional requirement | Customization required | Not Done
12.07 | 25% Benefit application | Individual document field be made available for all required documents | Additional requirement | Integration required | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
13 | Lump Sum/ Programmed withdrawal/ Annuity Benefit Applications | [6 empty] | 9 | 0 | 8 | 0 | 0
13.01 | Lump Sum/ Programmed withdrawal/ Annuity Benefit Applications | Ability to generate benefit consent on the benefit card | Initial requirement | Integration required | Not Done
13.02 | Lump Sum/ Programmed withdrawal/ Annuity Benefit Applications | Ability to reupload document for individual document fields. | Initial requirement | Integration required | Not Done
13.03 | Lump Sum/ Programmed withdrawal/ Annuity Benefit Applications | All document fields should be available after upload of partial documents. | Initial requirement | Integration required | Not Done
13.04 | Lump Sum/ Programmed withdrawal/ Annuity Benefit Applications | Some required fields should be made optional. | Initial requirement | Customization required | Not Done
13.05 | Lump Sum/ Programmed withdrawal/ Annuity Benefit Applications | Ability to flag multiple benefit request logged for client on workflow to avoid duplicate submission for a single client. | Initial requirement | Integration required | Not Done
13.06 | Lump Sum/ Programmed withdrawal/ Annuity Benefit Applications | Ability to auto populate document fields with existing documents | Initial requirement | Customization required | Not Done
13.07 | Lump Sum/ Programmed withdrawal/ Annuity Benefit Applications | Ability for the system to enhance resolution of documents sent by CX and same received at BAU's end to address issues of blurry images. | Initial requirement | Integration required | Not Done
13.08 | Lump Sum/ Programmed withdrawal/ Annuity Benefit Applications | Individual document field be made available for all required documents | Initial requirement | Integration required | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
14 | Additional Voluntary contribution | [6 empty] | 30 | 0 | 8 | 0 | 0
14.01 | Additional Voluntary contribution | Ability to generate AVC consent form. |  |  | Not Done
14.02 | Additional Voluntary contribution | some field mandatory fields should be made optional for additional AVC |  |  | Not Done
14.03 | Additional Voluntary contribution | Ability to auto populate documents fields with existing documents |  |  | Not Done
14.04 | Additional Voluntary contribution | Individual document field be made available for all required documents |  |  | Not Done
15 | Enbloc | [6 empty] | 73 | 0 | 8 | 0 | 0
15.01 | Enbloc | Ability to reupload document for individual document fields. |  |  | Not Done
15.02 | Enbloc | All document fields should be available after upload of partial documents. |  |  | Not Done
15.03 | Enbloc | Some required fields should be made optional |  |  | Not Done
15.04 | Enbloc | Ability to flag multiple benefit request logged for client on workflow to avoid duplicate submission for a single client |  |  | Not Done
15.05 | Enbloc | Ability to auto populate documents fields with existing documents |  |  | Not Done
15.06 | Enbloc | Ability for the system to enhance resolution of documents sent by CX and same received at BAU's end to address issues of blurry images. |  |  | Not Done
15.07 | Enbloc | Individual document field be made available for all required documents |  |  | Not Done
16 | Pre-scheme Benefit Application | [6 empty] | 71 | 0 | 8 | 0 | 0
16.01 | Pre-scheme Benefit | Ability to reupload document for individual document fields.
16.02 | Pre-scheme Benefit | All document fields should be available after upload of partial documents. |  |  | Not Done
16.03 | Pre-scheme Benefit | Some required fields should be made optional |  |  | Not Done
16.04 | Pre-scheme Benefit | Ability to flag multiple benefit request logged for client on workflow to avoid duplicate submission for a single client |  |  | Not Done
16.05 | Pre-scheme Benefit | Ability to auto populate documents fields with existing documents |  |  | Not Done
16.06 | Pre-scheme Benefit | Ability for the system to enhance resolution of documents sent by CX and same received at BAU's end to address issues of blurry images. |  |  | Not Done
16.07 | Pre-scheme Benefit | Individual document field be made available for all required documents |  |  | Not Done
17 | Deceased Benefit Application | [6 empty] | 72 | 0 | 8 | 0 | 0
17.01 | Deceased Benefit | Ability to reupload document for individual document fields. |  |  | Not Done
17.02 | Deceased Benefit | All document fields should be available after upload of partial documents. |  |  | Not Done
17.03 | Deceased Benefit | Some required fields should be made optional. |  |  | Not Done
17.04 | Deceased Benefit | Additional document fields should be added. |  |  | Not Done
17.05 | Deceased Benefit | Ability to flag multiple benefit request logged for client on workflow to avoid duplicate submission for a single client. |  |  | Not Done
17.06 | Deceased Benefit | Ability to auto populate document fields with existing documents. |  |  | Not Done
17.07 | Deceased Benefit | Ability for the system to enhance resolution of documents sent by CX and same received at BAU's end to address issues of blurry images. |  |  | Not Done
17.08 | Deceased Benefit | Individual document field be made available for all required documents |  |  | Not Done
18 | PW Enhancement. Monthly pension increment | [6 empty] | 70 | 0 | 8 | 0 | 0
18.01 | PW Enhancement. Monthly pension increment | Ability to reupload document for individual document fields.
18.02 | PW Enhancement. Monthly pension increment | 2. All document fields should be available after upload of partial documents.
18.03 | PW Enhancement. Monthly pension increment | 3. Ability to generate Enhancement form on the benefit card.
18.04 | PW Enhancement. Monthly pension increment | 4. Ability to flag multiple benefit request logged for client on workflow to avoid duplicate submission for a single client.
18.05 | PW Enhancement. Monthly pension increment | 5. Ability to auto populate document fields with existing documents
18.06 | PW Enhancement. Monthly pension increment | 6. Ability to auto populate document fields with existing documents
18.07 | PW Enhancement. Monthly pension increment | 7.Ability for the system to enhance resolution of documents sent by CX and same received at BAU's end to address issues of blurry images.
18.08 | PW Enhancement. Monthly pension increment | 8.Individual document field be made available for all required documents
19 | Retiree transfer to Annuity | [6 empty] | 67 | 0 | 8 | 0 | 0
19.01 | Retiree transfer to Annuity | Ability to reupload document for individual document fields.
19.02 | Retiree transfer to Annuity | All document fields should be available after upload of partial documents.
19.03 | Retiree transfer to Annuity | Ability to generate consent form on the benefit card
19.04 | Retiree transfer to Annuity | Ability to flag multiple benefit request logged for client on workflow to avoid duplicate submission for a single client.
19.05 | Retiree transfer to Annuity | Ability to auto populate document fields with existing documents
19.06 | Retiree transfer to Annuity | Ability for the system to identify and restrict request less than 1 year on PW
19.07 | Retiree transfer to Annuity | Ability to workflow annuity cancellation request to benefit
19.08 | Retiree transfer to Annuity | Ability for the system to enhance resolution of documents sent by CX and same received at BAU's end to address issues of blurry images.
19.09 | Retiree transfer to Annuity | Individual document field be made available for all required documents
20 | Additional Enbloc | [6 empty] | 65 | 0 | 8 | 0 | 0
20.01 | Additional Enbloc | . Ability to reupload document for individual document fields.
20.02 | Additional Enbloc | 2. All document fields should be available after upload of partial documents.
20.03 | Additional Enbloc | 3. some required fields should be made optional
20.04 | Additional Enbloc | 4. Ability to flag multiple benefit request logged for client on workflow to avoid duplicate submission for a single client
20.05 | Additional Enbloc | 5. Ability to auto populate documents fields with existing documents
20.06 | Additional Enbloc | 6.Ability for the system to enhance resolution of documents sent by CX and same received at BAU's end to address issues of blurry images.
20.07 | Additional Enbloc | 7.Individual document field be made available for all required documents
21 | Additional Lumpsum/PW | [6 empty] | 57 | 0 | 8 | 0 | 0
13.01 | Additional Lumpsum/PW | 1. Ability to generate benefit consent on the benefit card
13.02 | Additional Lumpsum/PW | 2. Ability to reupload document for individual document fields.
13.03 | Additional Lumpsum/PW | 3. All document fields should be available after upload of partial documents.
13.04 | Additional Lumpsum/PW | Some required fields should be made optional.
13.05 | Additional Lumpsum/PW | Ability to flag multiple benefit request logged for client on workflow to avoid duplicate submission for a single client.
13.06 | Additional Lumpsum/PW | Ability to auto populate document fields with existing documents
13.07 | Additional Lumpsum/PW | Ability for the system to enhance resolution of documents sent by CX and same received at BAU's end to address issues of blurry images.
13.08 | Additional Lumpsum/PW | Individual document field be made available for all required documents
22 | Additional AVC | [6 empty] | 54 | 0 | 8 | 0 | 0
21.1 | Additional AVC | Ability to generate AVC consent form.
21.2 | Additional AVC | some field mandatory fields should be made optional for additional AVC
21.21 | Additional AVC | Ability to auto populate documents fields with existing documents
21.22 | Additional AVC | Individual document field be made available for all required documents
23 | NSITF Request after Enbloc/Lumpsum/ PW withdrawal | [6 empty] | 53 | 0 | 8 | 0 | 0
23.01 | NSITF Request after Enbloc/Lumpsum/ PW withdrawal | Ability to reupload document for individual document fields.
23.02 | NSITF Request after Enbloc/Lumpsum/ PW withdrawal | 2. All document fields should be available after upload of partial documents.
23.03 | NSITF Request after Enbloc/Lumpsum/ PW withdrawal | 3. some required fields should be made optional
23.04 | NSITF Request after Enbloc/Lumpsum/ PW withdrawal | 4. Ability to flag multiple benefit request logged for client on workflow to avoid duplicate submission for a single client
23.05 | NSITF Request after Enbloc/Lumpsum/ PW withdrawal | 5. Ability to auto populate documents fields with existing documents
23.06 | NSITF Request after Enbloc/Lumpsum/ PW withdrawal | 6.Ability for the system to enhance resolution of documents sent by CX and same received at BAU's end to address issues of blurry images.
23.07 | NSITF Request after Enbloc/Lumpsum/ PW withdrawal | 7.Individual document field be made available for all required documents
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
24 | Exit from Scheme | [6 empty] | 36 | 0 | 8 | 0
24.01 | Exit from Scheme | Ability to reupload document for individual document fields. |  |  | Not Done
24.02 | Exit from Scheme | All document fields should be available after upload of partial documents. |  |  | Not Done
24.03 | Exit from Scheme | Some required fields should be made optional |  |  | Not Done
24.04 | Exit from Scheme | Ability to flag multiple benefit request logged for client on workflow to avoid duplicate submission for a single client |  |  | Not Done
24.05 | Exit from Scheme | Ability to auto populate documents fields with existing documents |  |  | Not Done
24.06 | Exit from Scheme | Ability for the system to enhance resolution of documents sent by CX and same received at BAU's end to address issues of blurry images. |  |  | Not Done
24.07 | Exit from Scheme | Individual document field be made available for all required documents |  |  | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
25 | Pre scheme Benefit - Intercontinental | [6 empty] | 33 | 0 | 8 | 0
25.01 | Pre scheme Benefit - Intercontinental | Ability to reupload document for individual document fields. |  |  | Not Done
25.02 | Pre scheme Benefit - Intercontinental | All document fields should be available after upload of partial documents. |  |  | Not Done
25.03 | Pre scheme Benefit - Intercontinental | Some required fields should be made optional |  |  | Not Done
25.04 | Pre scheme Benefit - Intercontinental | Ability to flag multiple benefit request logged for client on workflow to avoid duplicate submission for a single client |  |  | Not Done
25.05 | Pre scheme Benefit - Intercontinental | Ability to auto populate documents fields with existing documents |  |  | Not Done
25.06 | Pre scheme Benefit - Intercontinental | Ability for the system to enhance resolution of documents sent by CX and same received at BAU's end to address issues of blurry images. |  |  | Not Done
25.07 | Pre scheme Benefit - Intercontinental | Individual document field be made available for all required documents |  |  | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
26 | MULTIFUND TRANSFER Required View | [6 empty] | 29 | 0 | 8 | 0 | 0
26.01 | Mulitfund Transfer View | Multifund Transfer request |  |  | Not Done
26.02 | Mulitfund Transfer View | Multifund transfer request sent for approval. |  |  | Not Done | This should be an automated process. At what point are we sending request for approval?
26.03 | Mulitfund Transfer View | Multifund Transfer request approved. |  |  | Not Done
26.04 | Mulitfund Transfer View | Multifund Transfer request rejected. |  |  | Not Done
26.05 | Mulitfund Transfer View | Ability to auto update fund type based on change in date of birth |  |  | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
27 | MICRO PENSION SCHEME | [6 empty] | 23 | 0 | 8 | 0 | 0
27.01 | MicroPension Scheme | New MPS account change request. |  |  | Not Done
27.02 | MicroPension Scheme | MPS withdrawals. |  |  | Not Done
27.03 | MicroPension Scheme | Rejected MPS withdrawals. |  |  | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
28 | SLA | [6 empty] | 10 | 0 | 8 | 0 | 0
28.01 | SLA | System should escalate to supervisors where TAT has exceeded for all parties involved in the benefit process (CX/BWU/Compliance) |  |  | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
29 | Accept or reject Rejections | [6 empty] | 51 | 0 | 8 | 0 | 0
29.01 | Accept or reject Rejections | System should have the ability to highlight and allow users return rejected ALL applications types to BWU. |  |  | Not Done
29.02 | Accept or reject Rejections | Application should go to supervisor for review before it’s sent to BWU |  |  | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
30 | Confirmation letter process | [6 empty] | 7 | 0 | 8 | 0
30.1 | Confirmation letter process | System should track employer confirmation letter for relevant application types. |  |  | Not Done
30.2 | Confirmation letter process | System would be automated to trigger the e-mail to employers via the employer's predefined e-mail address on the system. |  |  | Not Done | SMS should also be used as an alternative to e-mail address
30.3 | Confirmation letter process | RM and Client would be copied in the emails sent to employers. |  |  | Not Done
30.4 | Confirmation letter process | RM receive periodic reminders to follow up if no response is received from employer. |  |  | Not Done
30.5 | Confirmation letter process | Client to get separate mail with RM in copy stating response has not been received to allow client follow up where necessary |  |  | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
31 | Email and SMS option | [6 empty] | 5 | 0 | 8 | 0
31 | Email and SMS option | Ability to select clients preferred for transactional and none transactional notifications(SMS/Email). |  |  | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
32 | Call center Mass update process | [6 empty] | 4 | 0 | 8 | 0
32.01 | Call center Mass update process | Ability to upload collated update form the call center and send to DMU for update. |  |  | Not Done
32.02 | Call center Mass update process | Upon receipt of Mass upload, DMU to isolate and treat each update request as it applies to each client |  |  | Not Done
[8 empty] | Total | Done | Not Done | Deployed | Stepped Down
33 | Routing of expired SLA of client complaints to assigned employer BDE | [6 empty] | 3 | 0 | 8 | 0
33.011 | Routing of expired SLA of client complaints to assigned employer BDE | System to automatically assigned expired complaint SLA to BDEs assigned to the employer. |  |  | Not Done
34 | Web Client View
34.01 | Web Client View | Ability to view client's login information and activation code
Note on C88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependent on integration with ECRS
Note on C92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependent on BC integration with ECRS
Note on C93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: dependent on Subscription to app
Note on C111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CX to Provide Fields

## Reconciliation Unit Requirement
Ref | Function | Business Requirement | Requirement Type | BC Capability | Status | Details | Phase | Total | Done | Not Done | Deployed | Stepped Down
1 | Statement Generation | [7 empty] | 0 | 16 | 0 | 0
1.01 | Statement Generation | There are 3 options to be considered in generating and uploading bank statement: | Initial requirement |  | Not Done
1.01.1 |  | Integration with UPCL/ZPC to automatically request/generate Bank Statement |  |  | Not Done
1.01.2 |  | UPCL/UBA ability to successfully drop Bank statement in a secured SFTP location and ability for the system to Pick the Bank Statement from the SFTP |  |  | Not Done
1.01.3 |  | Users ability to upload Bank statement directly on the system |  |  | Not Done
1.02 |  | Ability to auto-notify all relevant units with a white label link to download the account statement |  |  | Not Done
2 | Reconcile Account Statements | [7 empty] | 0 | 16 | 0 | 0
2.01 |  | Ability to auto-reconcile uploaded statements and automatically create a workflow for debit transactions using the following conditions: |  |  | Not Done
2.01.1 |  | Same day Reversal transactions from the contribution accounts |  |  | Not Done
2.01.2 |  | Predefined day/date reversal from the reconciliation account. The system should automatically confirm if the employer’s remittance has been processed before Initiating contributions reversal |  |  | Not Done
3 | Archive reconciliation and contribution account statements | [7 empty] | 0 | 16 | 0 | 0
3.01 |  | System should automatically archive the uploaded statements on the system |  |  | Not Done
3.02 |  | Ability to retrieve a predefined reconciliation and contribution account statement for any specified period |  |  | Not Done
4 | BankSM Upload | [7 empty] | 0 | 16 | 0 | 0
4.01 |  | There are 2 options to be considered in generating and uploading bank statement: |  |  | Not Done
4.01.1 |  | System should be able to pick BankSM from a secured SFTP location and automatically upload into the system |  |  | Not Done
4.01.2 |  | Users ability to upload Bank statement directly on the system. |  |  | Not Done
5 | BANKSM reconciliation | [7 empty] | 0 | 16 | 0 | 0
5.01 |  | System auto reconcile BankSM and Bank Account Statement, ensuring all “Eligible Credit” line of transaction in the contribution account are accounted for in the BankSM and the BankSM does not have more transaction lines missing on the Bank Statement |  |  | Not Done
5.02 |  | System ability to automatically validate the employer code on the BankSM in comparism with Employer code on our system and throw exception to Users for lines of transactions with unmatching employer code. Users has the option to continue the process. |  |  | Not Done
5.03 |  | Systems ability to generate an exception report if discrepancies are noticed |  |  | Not Done
6 | Posting and archiving of BankSM SM | [7 empty] | 0 | 16 | 0 | 0
6.01 |  | The BankSM should be automatically posted into Employer Ledger Entries upon successful validations, the status of such transaction should read “No Scheduled” for lines of transactions with confirm/validated Employer code |  |  | Not Done
6.02 |  | For lines of transaction with no matching employer code on the system, the system should post same on the Employer Ledger with unknown employer code, the status of such transaction should be “No Employer” |  |  | Not Done |  |  | Total | Done | Not Done | Deployed | Stepped Down
6.03 |  | System should automatically archive the uploaded BankSM on the system |  |  | Not Done
6.04 |  | System ability to enable users retrieve a predefined BankSM for any specified period |  |  | Not Done
7 | Statement Batch Reallocation Workflow | [6 empty] | 8 | 0 | 7 | 0 | 0
7.01 |  | Systems should automatically update the Employer Code, Employer Name, and details on the Employer Ledger with the discovered Employer Code on the CTS detected during the CTS Upload by CPU team | Initial requirement |  | Not Done
7.02 |  | The details of the Reallocation (Time relocated, Former Employer Code, etc.) should be stored with the employer lines of transaction details | Initial requirement |  | Not Done
7.03 |  | Users ability to view Reallocation Report and Exception for any day and time | Initial requirement |  | Not Done
7.04 |  | Systems should automatically update the users ability to view and reprocess failed Batch Reallocation | Initial requirement |  | Not Done
8 | Reversal Workflow | [7 empty] | 0 | 16 | 0 | 0
8.01 |  | Users ability to callup transactions for a particular day or range of days based on the uploaded statement and Bank SM in the system | Initial requirement |  | Not Done
8.02 |  | Users ability to view Transactions lines from the above that are only eligible for reversal. Transactions lines that have not been impacted by any form of transactions | Initial requirement |  | Not Done
8.03 |  | Transactions history or trail should not be deleted in the system. However, status should indicate that it was manually reversed, and such transactions lines should not be available for any form of processing | Initial requirement |  | Not Done
8.04 |  | Users ability to process multiple line of Transactions for reversal |  |  | Not Done |  |  | Total | Done | Not Done | Deployed | Stepped Down
8.05 |  | Users ability to view report showing all reversed Transactions |  |  | Not Done
8.06 |  | The Reversal workflow should have a maker-checker functionality |  |  | Not Done
9 | Shortfall Workflow Register | [6 empty] | 10 | 0 | 9 | 0 | 0
9.01 |  | System ability to allow for pre-configuration of short fall threshold limit | Initial requirement |  | Not Done
9.02 |  | Ability to map a pre-defined short fall threshold limit to an Employer | Initial requirement |  | Not Done
9.03 |  | System ability to automatically generate entries into the shortfall workflow register once a shortfall has been detected. This is closely tight and coupled to the employer shortfall threshold defined above | Initial requirement |  | Not Done
9.04 |  | System ability to automatically process a shortfall based on a predefined Job | Initial requirement |  | Not Done
9.05 |  | Users ability to view report and details of the processed shortfalls | Initial requirement |  | Not Done
9.06 |  | The shortfall should be configured to be debited/offset from Admin Fee Charges | Initial requirement |  | Not Done
10 | RSA Refunds/Withdrawal Workflow | [6 empty] | 7 | 0 | 9 | 0 | 0
10.01 |  | Users ability to view all entries of line of open refund/withdrawals request | Initial requirement |  | Not Done
10.02 |  | Users ability to review all supporting documents and view all transactions lines attached to each refund types and batch | Initial requirement |  | Not Done
10.03 |  | The Refunds/Withdrawal workflow show have a makerchecker functionality | Initial requirement |  | Not Done
10.04 |  | System ability to automatically post the refund transaction, alongside all Pre-CRA interest elements |  |  | Not Done
11 | MPS Reconciliation | [6 empty] | 6 | 0 | 9 | 0 | 0
11.01 |  | System ability to reconcile transactions lines and amount that impacted MPS contribution Account for actual MPS transaction processed |  |  | Not Done
11.02 |  | System should prevent RU Personnel from performing a new reconciliation, once there is an open exception that has not been pushed to register |  |  | Not Done
12 | Creation of Partially processed Processed Reason Code and Description Processed Reason Code and Description | [6 empty] | 2 | 0 | 2 | 0 | 0
12.01 |  | System ability to create partially processed reasons code and corresponding description |  |  | Not Done
12.02 |  | System should ensure prevention of multiple partially processed reason code |  |  | Not Done | system should avoid duplication of partially processed reason code
12.03 |  | System ability to edit existing partially processed reason code |  |  | Not Done
13 | Posting of Pre-Cra (inception Interest accrued on the money (pre-cra) | [6 empty] | 2 | 0 | 2 | 0 | 0
13.01 |  | System ability to edit existing partially processed reason code | Initial requirement |  | Not Done
13.02 |  | System ability to allow users create Pre-Cra refund card | Initial requirement |  | Not Done
13.03 |  | System ability to allow selection of bank entry that relates to Pre-Cra uploaded on Navision |  |  | Not Done
13.04 |  | Ability for users to modify date of debit |  |  | Not Done
13.05 |  | System capability to Post refund card created |  |  | Not Done

## CPU Requirements
Ref | Function | Business Requirement | Requirement Type | BC Capability | Status | Details | Phase |  | Total | Done | Not Done | Deployed | Stepped Down
| Contribution Processing |  |  |  | Not Done
14 | CTS Upload, Validation, Reconciliation, Allocation and Reallocation | [7 empty] | 60 | 0 | 17 | 0 | 0
14.01 |  | System ability to receive CTS feeds & CTS summary from Custodian (UPCL/ZPC) unto theSystem. | Initial requirement |  | Not Done
14.02 |  | Where there is an employee ID match, the System should be able to automatically reconcile the CTS and CTS Summary for the corresponding amount to be posted into ledger entry for client | Initial requirement |  | Not Done
14.03 |  | System should automatically display an exception report with the exact lines to aid correction process with the Custodian | Initial requirement |  | Not Done
14.04 |  | System should automatically archive the CTS and CTS Summary uploaded for reporting, immediate and future reference. | Initial requirement |  | Not Done
14.05 |  | At CTS upload,System should replace all prefix ‘UBA’ and other Non-PEN Prefixes with PEN). | Initial requirement |  | Not Done
14.06 |  | Users ability to Mark/Check available processing officers’ names for which unmatched Transaction is to be allocated to |  |  | Not Done
14.07 |  | System ability to detect foreign character and display the exact lines for ease of correction |  |  | Not Done
14.08 |  | System ability to detect lines of employer codes that are not in our database from the CTS, such transaction lines are to be displayed to the processor for instant correction |  |  | Not Done
14.09 |  | System ability to detect line of transactions where employee leg is greater than employer legs and employer legs are not zero |  |  | Not Done
14.1 |  | System ability to do a batch PIN reconciliation or PIN on CTS viz-a-viz PIN on DB |  |  | Not Done
14.11 |  | System ability to auto-populate all required fields subject to information derived from the CTS, CTS Summary, etc. |  |  | Not Done
14.14 |  | System should be able to manage PIN reconciliation. The business rules will be defined during process andSystem design |  |  | Not Done
14.13 |  | System ability to automatically retrieved all fees and charges as defined within the Employer Attribute required to process all transactions |  |  | Not Done
14.14 |  | System ability to automatically process reconciled CTS to transaction posting review stage |  |  | Not Done
14.15 |  | System ability to allow processing of CTS Lines of transactions with Multiple Statement lines—Schedule |  |  | Not Done
14.16 |  | System ability to auto send eligible transaction to approval stage |  |  | Not Done
14.17 |  | System ability to maintain total process transaction and outstanding transactions balance in the approval stage header view |  |  | Not Done
15 | Reconciliation and Error (processing CTS Transactions that failed PIN validation and matching) | [6 empty] | 1 | 0 | 17 | 0 | 0
15.01 |  | System ability to create and maintain a meta dictionary that stores all manually corrected Names, (This meta dictionary maintains the new Name correction. The system can consistently use this meta dictionary in subsequent PIN Name Validation)
15.02 |  | System ability to allow processor/Users auto correct Unprocessed line of transactions directly from the system and sent same for reviews.
15.03 |  | System ability to group and batch transaction line using Employer Code, Schedule/Cash ID. This equally gives the processor/Users the opportunity to see transaction in approval stage, however, users can not work on such transactions.
15.04 |  | CPU Supervisor should be able to auto view FDR used in processing manual reconciliation and correction
16 | Auto Processing | [6 empty] | 1 | 0 | 17 | 0 | 0
16.01 |  | System ability to auto post transaction lines anytime price is discovered on the system.
16.02 |  | System ability to automatically triggered SMS to clients during processing
16.03 |  | System ability to automatically Generate Reports (Listing, Pricing, Consolidated FDR). Send and make all Report to stakeholders (Manual), Transaction Notification Report
17 | Multi-Fund Transfer workflow Workflow | [7 empty] | 47 | 0 | 17 | 0 | 0
17.01 |  | Ability to review Fund ID movement on each Multi-Fund batch to ensure compliance. |  |  |  | System ability to allow users (CX Primary and CPU) to enter a multi-fund Transfer Request
17.02 |  | Ability to open each logged transfer card on Multi-Fund List module to change posting date to current transaction date and revalidate. |  |  |  | System ability to automatically create Multifund Transfer request base on the existing business rules (i.e., Clients attaining the age of 50).
17.03 |  | Ability to post each revalidated card (At posting, the system runs and sends SMS and E-mail notification to clients involved |  |  |  | Users ability to upload, retrieve and view supporting documents
17.04 |  | Ability to run Multi-fund exception report to confirm all postings are posted |  |  |  | This process should enforce a maker-checker functionality using the below rules (CX -CPU) or (CPU1 – CPU2)
17.05 |  | Where there are no exceptions, run Multi-Fund transfer report for each fund transfer and send to stakeholders |  |  |  | System ability to allow the checker to view the request and automatically send for processing singularly or multiple records.
18 | Processing of Unprocessed Money | [7 empty] | 20 | 0 | 0 | 0 | 0
18.01 |  | • Unprocessed Monies are transactions line we are unable to process at the original time of processing for one reason or the other
18.02 |  | • Users ability to correct/Amend, i.e. (PINs, Staff ID, and Name of Employees) Unprocessed Reasons and send same for approval and auto processing
18.03 |  | • Users Ability (CPU/RU) to send Unprocessed Money lines of Transaction/Batches to Refunds workflows when requests are received from (Employers, Historical Records, PenCom and Historical Data)
18.04 |  | • Users Ability to correct Unprocessed reasons
18.05 |  | • System functionality to ensure maker-checker functionalities
18.06 |  | • Users ability to attach and retrieve supporting documents to aid approval process
18.07 |  | • System ability to indicate that a transaction lines or Batch are been worked on by another actor/user
18.08 |  | System should have ability to identify/link each partially processed pin/details with the initial PFA it was previously transferred to.
19 | Micro Pension Contribution Processing | [7 empty] | 23 | 0 | 0 | 0 | 0
19.01 |  | • Receive contribution with clients’ details on the contributions register of Micro Pension Module as soon as the payment is made at the bank or any other payment platform.
19.02 |  | • System Ability to queue contributions until batched (The system batches every transaction on queue within 30 minutes of receipt).
19.03 |  | • System ability to keep Contributions in a queue until batched
19.04 |  | • System ability to batch transaction on queue within 30 minutes of receipt
19.05 |  | • Functionality to allow users batch the contributions manually by clicking on the “Contributions Batcher Job”. Where the contribution(s) are not batched
19.06 |  | • System feature to allow batched contributions processing using the current price date.
19.07 |  | • System ability to process every transaction as soon as batched
19.08 |  | • Where the contribution(s) are not processed, system ability to allow CPU officer to process the contributions manually by clicking on the “Contributions Post Job”.
19.09 |  | • System ability to send SMS notification immediately the transaction is processed (real time)
19.1 |  | • System ability to receive unreconciled transactions from RU for processing immediately
19.11 |  | • Steps above is repeated until the cut-off time of 4.00pm.
19.12 |  | • All unreconciled transactions are received from RU the following day on NAV and processed accordingly.
20 | Processing of PIN Change and Merger | [7 empty] | 19 | 0 | 0 | 0 | 0
20.01 |  | • System ability to allow Users setup PIN Change, PIN Merger Request
20.02 |  | • These Module should include a maker- checker features
20.03 |  | • System Ability to allow attachment and retrievals of supporting documents
20.04 |  | • System ability to automatically process PIN Change and Merger request using the logic specify in Appendix |  |  |  | Movement should reflect on Ledger entries for clients involved.
20.05 |  | System Ability to register cash movement by log for Fund Accounts Review |  |  |  | Movement should reflect on RSA statement for clients involved.
20.05 |  | System should restrict pin change for client’s that has pending benefit application request, prompting CPU to seek further clarification from BAU |  |  |  | Contribution summary should reflect the new position after movement.
20.05 |  | Total unit is to be liquidated at the prevailing unit price to buy unit in another fund at the current price.
20.05 |  | Ability to send notification from PIN Change Module to RU for PIN block.
21 | Reprocessing of returned contributions | [7 empty] | 10 | 0 | 0 | 0 | 0
21.01 | NEFT Return Processing | • Auto processing of Neft Return Processing and Auto Pushing of Neft Return to Neft Return register.
21.02 | Workflows (Fund 1, Fund 11, 111, IV, VI) | • System ability to allow users push records to Neft Return for upward processing by CPU
21.03 |  | • System ability to receive Neft return feeds from UPCL
21.04 |  | • System Ability to perform auto reconciliation with existing database record for specified PINs
21.05 |  | • System ability to auto process based on correct validation
22 | Contribution batch Reversal / Partially Processed Reversal | [7 empty] | 4 | 0 | 0 | 0 | 0
22.01 |  | • System Ability to perform Reversal before Pricing /EOD
22.02 |  | • System Ability to perform Reversal After EOD/
22.03 |  | • System Ability to perform Contribution batch reversal – all
22.04 |  | • System Ability to perform Partially processed reversal --- unprocessed
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
10 | [8 empty] | 0 | 0 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
11 | [8 empty] | 1 | 0 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
13 | [8 empty] | 0 | 0 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
13 | [8 empty] | 1 | 0 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
14 | [8 empty] | 1 | 0 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
15 | [8 empty] | 5 | 0 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
16 | [8 empty] | 6 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
17 | [8 empty] | 7 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
18 | [8 empty] | 7 | 0 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
19 | [8 empty] | 6 | 0 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
20 | SLA | [7 empty] | 2 | 0 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
21 | Accept or reject Rejections | [7 empty] | 2 | 0 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
22 | Confirmation letter process | [7 empty] | 1 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
23 | Email and SMS option | [7 empty] | 2 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
24 | Call center Mass update process | [7 empty] | 1 | 0 | 0 | 0
[9 empty] | Total | Done | Not Done | Deployed | Stepped Down
25 | Routing of expired SLA of client complaints to assigned employer BDE | [7 empty] | 0 | 0 | 0 | 0
Note on B22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This process details the business requirement for processing CTS Transactions that failed PIN validation and matching during the upload process. It equally details the requirement to manually correct transactions line that are already auto process to the transaction posting review stage.
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The Auto Processing stage is the system ability to auto post transaction lines anytime price is discovered on the system.
Note on G32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reccommendation by BA team

## Refund Unit Requirements
Ref | Function | Business Requirement | Requirement Type | BC Capability | Status | Details | Phase | Total | Done | Not Done | Deployed | Stepped Down
Refund Unit
23 | Refund Unit / Partially Processed Reversal | [6 empty] | 47 | 0 | 0 | 0 | 0
23.01 | Double Registration | Upon validation of ARM duplicate pins, the system should be designed that - ARM duplicate PINs can be merged with a click of button and a prompt for authorization |  |  |  | · User(s) Ability to select single line/batched lines of transactions for refunds from partially and unprocessed views based on the below criteria’s (Unprocessed reasons, Fund Types, Fund Price, etc) and send such transactional refund request to Refund-Transfer workflow
23.02 | For Multiple PINs between PFAs | System design for ability to: |  |  |  | · Users ability to define refund type request and attach supporting documents as required on desired refund-transfer transaction and view auto generated schedules
23.03 |  | § Instruction received, via process tracker, spool all remittance in the invalid pins and initiate withdrawal document. |  |  |  | · System ability to batch all transaction according to the business rule defined in appendix 1.0 (Batched by PFAs, etc.)
23.04 |  | § Send to Refund and RU supervisor for review |  |  |  | · System ability to automatically generate schedules
23.05 |  | § Mandate is generated and send to signatories then custodian |  |  |  | · Users ability to send refund-transfers for approvals
23.06 | For State & FCTA/FCDA refund | Upon instruction through process tracker or employer managers, the following should be done |  |  |  | This system should be a maker -checker system
23.07 |  | ARM account validation tool kits should be modified to allow validation of various account number without bank sort code.
23.08 |  | The system should be able to generate, or spool contribution of employee & employer and interest earn on each (interest on employee and employer), total interest and price, the Fund client belong.
23.09 |  | § Proceed to paperless to generate mandate and send to signatories for approval.
23.1 |  | § Upon posting by BAU, a mandate should be generated on paperless to State bureau notifying that refund has been completed.
23.11 | § PenCom Refund | § Withdrawal process
23.12 |  | § The system should be designed that all withdrawal process should be done on the system.
23.13 |  | § The system should be able to separate PenCom contribution from other source, prepare breakdown for based on PenCom template with percentage requested.
23.14 |  | § System ability to generate mandate on Paperless and send to signatories for approval
23.15 |  | § Prompt custodian to provide RTGS for such transaction.
23.16 | § PenCom Refund Unapplied | § System ability to accommodate various bank entry number in one refund card – batch upload
23.17 |  | § System ability to generate mandate, send to signatories, custodian and send notification upon posting by RU.
23.18 | § Refund to NPF | § System ability to accommodate various bank entry number in one refund card – batch upload
23.19 |  | § System ability to generate mandate, send to signatories, custodian and send notification upon posting by RU.
23.2 | § Refund to NPF – Withdrawal | § System ability to initiate withdrawal process and giving room to process owner to select price date irrespective of the client fund.
23.21 |  | § System ability to provide withdrawal breakdown
23.22 |  | § System ability to generate mandate after upon withdrawal approval by refund and RU supervisor.
23.23 |  | § System ability to send mandate to custodian upon signatories’ approval. | [5 empty] | Total | Done | Not Done | Deployed | Stepped Down
23.24 | § Refund to employees. | § System ability to separate employee contribution from employer, calculate unit, initiate withdrawal (both batch and single withdrawal).
23.25 |  | § System ability to generate mandate after upon withdrawal approval by refund and RU supervisor.
23.26 |  | System ability to send mandate to custodian upon signatories’ approval.
23.27 | Transfers | The system should be built with Artificial Intelligence in such a way that all initially Identified Pins status should be flagged with their respective PFA (note that this might be from Pencom List, Project of Identifying correct Pin) will generate a report after RSA report has been submitted. In this way RM can collate monthly and send to employers for clarifications.
23.28 |  | The idea of Uploading cards and Inserting from unprocessed monies can be eradicated by creating CSV’s that will speak to Individual Pins, Names, Entry No’s and Bank Statement.
23.29 |  | · Please note that only Refund Type name and Account will be inserted manually.
23.3 |  | · The system will speak to all lines of transaction when it is been posted.
23.31 |  | · Instructions will be generated by design already on the system, per PFA and their respective amount.
23.32 |  | · Signatories will sign
23.33 |  | · Once this logged an automated process will send to Custodian with corresponding Schedules
23.34 |  | Update of partially processed should be done automatically to reflect live position of Nomenclature.
24 | Others | [6 empty] | 1 | 0 | 0 | 0 | 0
24.01 | üDaily monitoring of all RSA Investment account and retiree investment account for inflows & sending of withdrawal posting to benefit. üShortfall posting üMonthly Interest Payment into client RSA. üUpdating to current nomenclature while creating refund cards e.g. (Shortfalls, Fundmismatch, NDB). üNDB projects. | Daily monitoring of statement. - System ability to allow uploading of daily posting details using template provided CPU and Dependencies. - Monthly Interest Payment into client RSA
24.02 |  | System ability to spool report and generate mandate (instruction), prepare schedule based on pins subtotal, and send to refund supervisor for approval. Thereafter to Signatories for signing.
25 | Contributions processed by Refund | [6 empty] | 1 | 0 | 0 | 0 | 0
25.01 |  | System ability to receive CTS like UPCL feeds from ZPC custodian will facilitate a seamless process as against creation of CVSs that we currently run.
25.02 |  | Notification upon crediting of ZPC transaction should be automated such that dependent unit i.e (BAU/Compliance dept) is aware and fully updated. This will reduce the pain of asking or sending emails and also reduce TAT.
26 | Transfer to AVC | [6 empty] | 1 | 0 | 0 | 0 | 0
26.01 |  Withdrawal of mandatory contributions to AVC: _RSA to RSA  Withdrawal of mandatory contributions to AVC: _RSA to RF  Withdrawal of AVC contributions to mandatory: _RSA to RF  Withdrawal of AVC contributions to mandatory: _RF | When we have approval from PENCOM, the new system should allow Refund move lines of contribution from mandatory column to AVC column (Vice Versa). An example is the pin change module, this can run on the same logic if it’s same Fund.
26.02 |  | For different funds (i.e erroneous credit of AVC to another client’s account, documents will be sent to Custodian to move cash position)
27 | TCF transfers | [6 empty] | 1 | 0 | 0 | 0 | 0
27.01 | üCrediting No PIN transactions into TCF üTCF Withdrawal to RSA (ARM) üTCF Withdrawal to Other PFAs. | The system should be designed in a way that breakdown generated via Bi portal carries the period narration as stated on the contribution batch used in processing each line of transaction.
27.02 |  | The system should be able to generate a mandate which will be forwarded to the supervisor and other units for review and sign off. The mandate will be forwarded to the custodian.
27.03 |  | A schedule should be sent to UPCL consisting of the split contributions according to the initial period narrations which will be sent as summary.
27.04 |  | Creating of CTS by UPCL for processing contributions for TCF. The CTS will be assigned by authorizers for processing.
27.05 |  | The system should be designed in such a way that the bank entry number uploaded by RU on the statement will automatically be assigned to each CTS as soon as the CTS is being posted to contribution stage.
28 | Withdrawals | [6 empty] | 1 | #REF! | #REF! | #REF! | #REF!
28.01 | ü Withdrawal from RSA to RSA ü Withdrawal from RSA to RF ü Withdrawal from RSA to other PFA. | If clients are of the same fund, the system should be able to do transfer like Pin Change Logic, since there is no cash movement from One investment fund to another.
29 | Fundmismatch | [6 empty] | 1 | #REF! | #REF! | #REF! | #REF!
29.01 | Crediting client’s contribution into Refund Fund | The system should be designed in a way that breakdown generated via Bi portal carries the period narration as stated on the contribution batch used in processing each line of transaction
29.02 |  | · The system should be able to generate a mandate which will be forwarded to the supervisor and other units for review and sign off. The mandate will be forwarded to the custodian.
29.03 |  | · A schedule should be sent to UPCL consisting of the split contributions according to the initial period narrations which will be sent as summary.
29.04 |  | · Creating of cts by UPCL for processing contributions for retirees. The cts will be assigned by authorizers for processing.
29.05 |  | The system should be designed in such a way that the bank entry number uploaded by RU on the statement will automatically be assigned to each cts as soon as the cts is being posted to contribution stage.
Note on G5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reccomendation by BA Team

## Sheet2
Lead Creation on the GO
Start
Navigate to Lead Mangement module
User select Lead type
System Loads Lead type
Create New
Input Lead Type
Input Lead details
Qualify Lead

## Not Deployed
Ref | Function | Business Requirement | Requirement Type | CRM Capability | Status | Details | Phase
1.24 | Lead Management | Ability to create leads from Instagram | Additional requirement | Integration required | Not Done | API request rejected by Instagram | Phase 3
7.27 | Case Management | Ability to initiate withdrawal requests and upload supporting documents | Initial requirement | Integration required | Done | Redesign of Benefit Module on Business Central. | Phase 2

## Sheet1
To- Be Process Time Table |  |  | Requirement Type | CRM Capability | Status | Details | Phase | Total | Done | Not Done | Deployed | Stepped Down
Company and Time | Unit | Date | Requirement Type | CRM Capability | Status | Details | Phase | Total | Done | Not Done | Deployed | Stepped Down
ARM FUND ACCOUNT 9am - 4pm | BD (Sales, CX, MCC) | 22nd - 23rd Feb 2021
| DMU | 24 - 25th Feb 2021
| Investment Admin Contributions Refunds | 26th Feb, 1st -2nd March 2021
| BAU | 3rd - 5th March 2021
| Fund Account | 8th March 2021
| Compliance | 9th March 2021
| Risk Management | 10th March 2021
| Internal Audit | 11th March 2021
ARM COMPANY ACCOUNT 9am - 4pm | HR | 12th and 15th March 2021
| ADMIN | 16 - 17th March 2021
| Finance Company Account Intercompany Account | 18 - 20th March 2021

## Rules
Out-of-the-box functionality | Implemented | Initial requirement | Done | Phase 1
Customization required | Not implemented | Additional requirement | Not Done | Phase 2
Integration required | Stepped down |  | Deployed | Phase 3
Not Supported |  |  | Stepped Down